Brooklyn Outdoor Film Festival briefing.
Project Brief Client Name:
Client: Brooklyn Vibes Event Co.
Project: Brooklyn Park Movie Festival
Date: August 5 to August 8
Summary:

Brooklyn Vibes Event Co. will organize a three-day long Movie Event at the Brooklyn Park, the event is about to show films can appeal to audience of all ages and they want their advertisements and publications to reflect that same idea. We have a budget about $3.500 for the website and to communicate online in order to announce the upcoming shows and take reservations.

Project Team: Who will be working on that project?

Freelancer:
Developer: Daniel Schulreich

Brooklyn Vibes Event Co:
Jennifer Viala: Founder of Brooklyn Vibes Event Co.
John Doe: Social Media Communicator
Alissa Muster: Financial Assistant
Adam Volt: Multimedia Team (equip etc.)

Goal(s): What is the purpose? What are we trying to accomplish with this assignment?
Show that films can appeal to audience of all ages.
Advertisement and publications to reflect the same idea.
Reach limit of 5.000 reservations obtain with social Media.
Timeline:

Steps	Sub steps	Duration	Date
Meeting	Movie Genre and generation	2-hours	Mai.1
Movie selection	3-hours	Mai.1
Equipment organization	2-Weeks	Mai.1

Design Website	Presentation of layout and design	1-hours	Mai.15	Feedback and Ideas	2-hours	Mai.15

Create Website	Use Feedback to achieve final design	2-week	s	Mai.17
Create Version 1.0	3-weeks	June.1

Presentation	with Brooklyn Event Team	2-hours	June.25
Final design adjustment	1-hour	June.25

Finish Website	Admit final changes	3-days	June.27
Implement Movie Posters	---	June.27

Media campaign	Meeting finance and social media	2-hours
Launch Website	---
Start Social Media campaign	5-weeks	June.28
Invite Youtuber and magazines	June.28

Set up location	Equipment install and check	3-days	August,1

Event Start	5 August	August,5

Budget: We have a total budget of $3.500

 Core costs:
Salaries: Freelancer
Equipment for rent: Speakers, Screen
Services: Web hosting, domain
Social Media Campaign: Twitter, Instagram, Facebook, etc.